## Defect
Bug Name | Bug ID | Area Path | Build Number | Severity | Priority | Assigned to | Reported By | Reported On | Reason | Status | Data Used
Bar code is not accepting in the application | 1 |  | 0.1 | High | High | NA | Sammilkhan | 2016-03-11 | Defect | Open
Prices are not mentioned in the mail which is sent from application | 2 |  | 0.1 | High | High | NA | Sammilkhan | 2016-03-11 | Defect | Open
The prices are not as same as in the stores website | 3 |  | 0.1 | High | High | NA | Sammilkhan | 2016-03-11 | Defect | Open | CEDO for Moto G3 Motorola 3rd Generation - Toughene d Tempered Glass Screen Guard Protector
Application is not displayed products from all the stores. Some of the store are missing | 4 |  | 0.1 | High | High | NA | Sammilkhan | 2016-03-11 | Defect | Open
Major Icons (Home,BarCode,MailBox) is not displayed all screens | 5 |  | 0.1 | High | High | NA | Sammilkhan | 2016-03-11 | Defect | Open
Logo is not same in application and comparison mail | 6 |  | 0.1 | Low | Low | NA | Sammilkhan | 2016-03-11 | Defect | Open
Rupees Symbol is not present in the beginning of the amount | 7 |  | 0.1 | Low | Low | NA | Sammilkhan | 2016-03-11 | Defect | Open
There is no use of 'Enter you mail id' check box in mail window | 8 |  | 0.1 | Low | Low | NA | Sammilkhan | 2016-03-11 | Defect | Open
If there is only one store, It showing as 'Available from 1 Stores' | 9 |  | 0.1 | Cosmetic |  | NA | Sammilkhan | 2016-03-11 | Defect | Open
Lowest price has no appropriate value. It has 336 insatead of 336.00 | 10 |  | 0.1 | Cosmetic |  | NA | Sammilkhan | 2016-03-11 | Defect | Open